## Testing Road Map
Team 1 - Testing Scope
|  | Test Cycle 1 | Test Cycle 2 | Test Cycle 3
Xero Application Modules | Feature Backlog (from RCT) | Execution Ends - November 21 | Execution Ends - December 5 | Execution Ends - December 12
01. Dashboard
02. User Management and Authentication
03. Settings and Configuration
04. Financial Data Entry (Daniel Fox & Thyagaraj Raghava) | 04.01 Create General Ledger Accounts | X
| 04.02 Edit General Ledger Accounts | X
| 04.03 Record Journal Entries |  | X
| 04.04 Post Journal Entries |  | X
| 04.05 View Posted Journal Entries |  |  | X
| 04.06 Copy Journal Entries |  |  | X
| 04.07 Record Income Transactions |  | X
| 04.08 Record Expense Transactions |  | X
| 04.09 View Financial Ledger |  |  | X
| 04.10 Delete Or Reverse Entries |  |  | X
05. Bank Feeds and Reconciliations (Prashant Baral & Manisha Shah) | 05.01 Connect Bank Feeds | X
| 05.02 Import Bank Statements | X
| 05.03 View Feed Status | X
| 05.04 Match Statement Lines |  | X
| 05.05 Code Uncoded Lines |  | X
| 05.06 Create Bank Rules |  | X
| 05.07 Search Bank Rules |  | X
| 05.08 Record Transfers |  |  | X
| 05.09 Undo/Redo Reconciliations |  |  | X
06. Invoicing
07. Accounts Receivable
08. Purchase Orders (Arun Garwan & Deepali Sawant) | 08.01 Create Purchase Orders | X
| 08.02 Duplicate Purchase Orders | X
| 08.03 Update Purchase Orders | X
| 08.04 Approve Purchase Orders | X
| 08.05 View Purchase Orders | X
| 08.06 Delete Purchase Orders | X
| 08.07 Send Purchase Orders |  |  | X
| 08.08 Convert To Bills |  | X
| 08.09 Track Purchase Order Status |  | X
| 08.10 Print Purchase Orders |  |  | X
09. Expense Claims
10. Bills to Pay
11. Accounts Payable
12. Accounting Reports